## Project Planner
Desktop Application Project
[5 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Milestone 1 | 1 | 35 | 1 | 29 | 100%
1. Initiating | 1 | 7 | 1 | 5 | 100%
1.1 Form Group | 1 | 2 | 1 | 1 | 100%
1.2 Develop Project Charter | 3 | 4 | 2 | 3 | 100%
1.3 Meet with Stakeholders | 7 | 1 | 5 | 1 | 100%
2. Planning | 8 | 28 | 8 | 24 | 100%
2.1 Create Scope Plan | 8 | 3 | 8 | 3 | 100%
2.2 Create WBS and Gantt Chart | 11 | 4 | 11 | 3 | 100%
2.3 Fill out Project Management Plan | 15 | 7 | 14 | 5 | 100%
2.4 Fill out Software Design Document | 18 | 14 | 17 | 13 | 100%
2.4.1 System Vision Design | 18 | 3 | 17 | 2 | 100%
2.4.2 Requirements Design | 21 | 2 | 19 | 2 | 100%
2.4.3 Use Case Diagram&Descriptions | 23 | 2 | 21 | 2 | 100%
2.4.4 Software Design | 25 | 3 | 23 | 3 | 100%
2.4.5 System Components Descriptions&Design | 28 | 2 | 26 | 2 | 100%
2.4.6 User Interface Design | 30 | 2 | 28 | 2 | 100%
Milestone 2 | 32 | 28 |  |  | 0%
3. Executing | 32 | 13 |  |  | 0%
3.1 Implement Software Detailed Design | 32 | 2 |  |  | 0%
3.2 Implement Structural Design | 34 | 2 |  |  | 0%
3.3 Implement Visual Design | 36 | 2 |  |  | 0%
3.4 Make Changes in Github | 38 | 2 |  |  | 0%
3.5 Integrate Modules Application System | 40 | 2 |  |  | 0%
3.6 Test Application System | 42 | 3 |  |  | 0%
4. Controlling | 45 | 8 |  |  | 0%
4.1 Control&Develop Application System Quality | 45 | 3 |  |  | 0%
4.2 Status Analysis | 48 | 2 |  |  | 0%
4.3 Update Plans | 50 | 1 |  |  | 0%
4.4 Monitor Risks | 51 | 2 |  |  | 0%
5. Closing | 53 | 7 |  |  | 0%
5.1 Review&Complete Project Plan | 53 | 1 |  |  | 0%
5.2 Obtain User Formal Acceptance | 54 | 2 |  |  | 0%
5.3 Final Visual Application Performance | 56 | 2 |  |  | 0%
5.4 Verify Completion of Project | 58 | 1 |  |  | 0%
5.5 Archive Documents | 59 | 1 |  |  | 0%